## Sheet1
Tobin Completion Schedule
Note: Complete means bar non critical snags
Site | Complete By
Rosmuc
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Letterfrack
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Killimor
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Clifden
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Kilconnell
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Inishbofin
Civil | Civil works advanced far enough to allow commissioning of plant
Mechanical | Complete
Electrical | Awaiting ESB power up.
Commisioning | Estimated July 2012
Tir an Fhia
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Ballyconneely
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Estimated July 2012
Tully
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Carraroe
Civil | 31st March 2012
Mechanical | 9th March 2012
Electrical | Complete
Commisioning | Estimated July 2012
Oughterard
Mechanical | Complete
Electrical | Complete
Commisioning | Estimated July 2012
Spiddal
Mechanical | Complete
Electrical | Complete
Commisioning | Estimated July 2012
Portumna
Mechanical | Complete
Electrical | Complete
Commisioning | Estimated July 2012
Ballinasloe
Mechanical | Complete
Electrical | Complete
Commisioning | Estimated July 2012
RPS Revised Completion Schedule
Notes: Commissioning complete refers to end of 5 day test period
Complete means bar non critical snags
Site | Complete By
Leenane
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete (final testing required)
Woodford
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Plant on line
Inis Mor - Kilcarna
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Inis Mor- Cregacareen
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Inis Oirr
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete (treatment required to be confirmed)
Kinvara
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Estimated June 2012
Ryan Hanley Completion Schedule 29th Feb 2012
Note: Complete means bar non critical snags
Site | Complete By
Mid-Galway
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Mountbellew
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Ahascragh
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Ballygar
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Ballymoe
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Williamstown
Civil | Complete
Mechanical | Complete
Electrical | Complete.
Commisioning | Complete
Glenamaddy
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete
Dunmore/Glenamaddy
Civil | Complete
Mechanical | Complete
Electrical | Complete
Commisioning | Complete